Project planner uses periods for intervals. Start=1 is period 1 and duration=5 means project spans 5 periods starting from start period. Enter data starting in B5 to update the chart
Title of the project. Enter a new title in this cell. Highlight a period in H2. Chart legend is in J2 to AI2
Select a period to highlight in H2. A Chart legend is in J2 to AI2
Enter activity in column B, starting with cell B5
Enter plan start period in column C, starting with cell C5
Enter plan duration period in column D, starting with cell D5
Enter actual start period in column E, starting with cell E5
Enter actual duration period in column F, starting with cell F5
Enter the percentage of project completed in column G, starting with cell G5
Enter a period in the range of 1 to 60 or select a period from the list. Press ALT+DOWN ARROW to navigate the list, then ENTER to select a value
Type a value from 1 to 60 or select a period from the list-press CANCEL, ALT+DOWN ARROW, then ENTER to select a value
Periods are charted from 1 to 60 starting from cell H4 to cell BO4
This legend cell indicates plan duration
This legend cell indicates actual duration
This legend cell indicates the percentage of project completed
This legend cell indicates actual duration beyond plan
This legend cell indicates the percentage of project completed beyond plan
## Project Planner
Spilserver Administration
Select a period to highlight at right. A legend describing the charting follows.					Period Highlight:	5			Plan Duration					Actual Start					% Complete					Actual (beyond plan)					% Complete (beyond plan)
ACTIVITY	PLAN START	PLAN DURATION	ACTUAL START	ACTUAL DURATION	PERCENT COMPLETE	PERIODS
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60
Case Beskrivelse	1	1	1	1	100 %
Problem formulering	1	1	1	1	100 %
Kravspecifikation	2	1	2	1	100 %
Estimeret Tidsplan	2	1	2	1	100 %
Real Tidsplan	1	24	1	24	23 %
Processrapport	1	24	1	24	7 %
Produktrapport	1	24	1	24	5 %
Opsætning af Docker/DB	3	2	3	1	75 %
WebApi opsætning	4	3	4	3	50 %
K1 - API til åbne/lukke Docker containere	6	1	6	1	10 %
K2 - Opsætning og forståelse af flutter	7	7	7	7	0 %
K2 - Simpel app til administration af servere	10	7	10	7	0 %
K3 – Logning	8	1	8	1	3 %
K4 – Visning af online spillere/servere	9	2	9	2	5 %
K5 - Live opdatering i app	13	3	13	3	0 %
K7 - Automatiske backups af save-filer	16	2	16	2	0 %
K8 – Web-frontend	17	3	17	3	0 %
K9 - Push notifikationer	20	2	20	2	0 %
K10 – Brugerrettigheder	22	1	22	1	0 %